## Sheet1
Phase | Task | Status | Remarks
0 | Requirements Gathering & Sign-Off | Completed | Functional & non-functional requirements finalized
1 | System Architecture & DB Design | Completed | FastAPI + PostgreSQL + SQLAlchemy schema
2 | OTP Verification | Completed | OTP generation, validation, expiry handling
2 | User Registration & PDF Generation | Completed | Registration flow + PDF creation on submit
2 | Admin Authentication (JWT) | Completed | Secure admin login with token-based auth
2 | Admin Approval Workflow | Completed | Approve → Move to verified → Membership ID
2 | Advanced Filters & Search | Completed | State, district, mandal, gothram, surname, etc.
2 | Security, Validation & Error Handling | Completed | Auth guards, enums, validation, SQL fixes
2 | End-to-End Testing & Stabilization | Completed | Manual testing via Swagger & cURL
2 | OTP Verification through MSG91 | Pending | Need DLT type from organziation
2 | Email OTP verification through Brevo | Completed | OTP generation through brevo
2 | Testing workflow | Completed
3 | OTP Security Hardening | Completed | Resend cooldown, max attempts, OTP locking
3 | Admin Pagination | Completed | Page/size support with safe limits
3 | Status-Based User Listing | Completed | Pending / Approved / Hold / Rejected listings
3 | CSV Export (Admin) | Completed | Export users with full profile fields
3 | Registration Duplicate Protection | Completed | Prevent duplicate email/mobile registrations
3 | Admin Bulk Actions | Completed | Bulk approve, reject (with reason), hold
3 | Admin Audit Logs | Completed | Track admin actions with timestamp & reason
3 | Approval Email Notification | Completed | Auto email with Membership ID & greeting